## Spec
Specification |  |  |  | DO NOT EDIT THIS PAGE
Theme name: OTH201309 WebStore test name: OnTheHub WebStore test Account #: 100012038 Mock ups included: Yes |  | Notes: DO NOT EDIT THIS PAGE CHECK QA TRACKING 1 FOR FIXES FOR PREVIOUS TEST RESULTS USE QA TRACKING CYCLE 2 TO LOG NEW/ UNRESOLVED TESTS |  | Edit the most recent fix cycle
Term | Term Description | Term notes | Values | Values 2 | Additional Information | QA Resuts 1 | QA Resuts 1 comments | Fix Cycle 1 | Fix Cycle 1 Comments
Browsers | Browsers' refers to all of the browsers which need to be tested against. | This browser list has been created using the following four sources to determine which broswers represent our user population: Analytics from e5.onthehub.com http://en.wikipedia.org/wiki/Usage_share_of_web_browsers http://www.w3counter.com/globalstats.php?year=2013&month=009 http://www.w3schools.com/browsers/browsers_stats.asp | Windows: Internet Explorer 8 | Majority (split) | Internet Explorer has a wide range due to its variety of active versions and also because of specific business relationships
Windows: Internet Explorer 9
|  |  | Windows: Internet Explorer 10 | Majority (split)
Windows: Internet Explorer 11
|  |  | Windows: FireFox | Majority
|  |  | Windows: Chrome | Majority
|  |  | OSX: Chrome (Latest) | Majority
|  |  | OSX: Safari (Latest) | Majority
|  |  | OSX: FireFox (Latest) | Majority
Test Pages | Test Pages' refers to the minimum pages which can be used to test the entire webStore theme. This list requires that one instance of every available element and element combination in e5 be represented in the pages tested against. |  | ~/WebStore/Account/AcceptTermsOfService.aspx |  | This is a best guess until we can iron it out.
~/WebStore/Account/SdmDownloadFaq.aspx
~/WebStore/Account/OrderDetails.aspx
~/WebStore/Account/YourAccount.aspx
~/WebStore/Checkout/SelectBillingAddress.aspx
~/WebStore/Checkout/ConfirmOrder.aspx
~/WebStore/Common/ReviewOrderMessages.aspx
~/WebStore/OfferingDetails.aspx
~/WebStore/Welcome.aspx
~/WebStore/OfferingsOfMajorVersionList.aspx
~/WebStore/ProductsByMajorVersionList.aspx
~/WebStore/ProductSearchOfferingList.aspx
~/WebStore/Security/AcceptTermsOfService.aspx
~/WebStore/Security/Signin.aspx
SDM: On initial Page Load
SDM: After 'download' is clicked
Languages | Languages' refers to the different languages e5 supports. Every test should be run against the languages that are best described in the Values section. |  | English | Standard | This is a best guess until we can iron it out.
|  |  | Korean | Short standard
|  |  | Russian | Long Standard
Variants | Variants' refer to the explicit rules which should be checked to qualitate if a test case in the Visual section passes or not. | The 'varients' to the right are examples which you will see in the 'Variant' column in the 'Visual - Constants' worksheet. The cells to the right of each example variant explains it indepth. | Offset 10px | There can a limit of plus or minus of 10 pixels in the placement of the element in the webstore against the placement in the design. | Often with astetics there are threshholds which will and will not look appealing. These thresholds will need to be revisited and updated as they become more appearent through testing and user feed back loops. Open to suggestion on how to best communicate and agree on these 'soft' thresholds.
|  |  | Not breaking container | The element in question is not 'breaking out' of a visual container. Such as a title overlapping a container with a border around it. Or a menu overlapping a banner.
|  |  | Font face | Confirm the elements font family
|  |  | Font size | Confirm the elements font size visually (within reason)
|  |  | Color | Confirm the color
Inspector | Inspector' refers to the tools within each browsers' built in or thirdparty developer tools which allows you to view and analyze the HTML, CSS, javascript and processings of a webpage. The inspector should be used to verify CSS properities. |  |  |  | Like the 'console' each browser has it's own 'inspector' they all complete the same task but have slightly differernt user interfaces.
Console | Console' refers to the in browser area where you can check to see javascript errors. | In Chrome you open 'developer tools' and click on the 'console' pane. In Internet Explorer you open 'developer tools' and click on the 'console' pane. In FireFox you open 'Web Console' from the tools menu |  |  | All browsers have a 'Console' they are all a little bit different but the function of them is to see output from the browser.

## Tests - Constants
VISUAL - Constants |  | Overview of the common theme elemenet that span multiple pages and are common amoung all e5 themes. |  | DO NOT EDIT THIS PAGE
Notes: THIS PAGE IS A REFERENCE FOR THE TEST CASES DO NOT EDIT THIS PAGE CHECK QA TRACKING 1 FOR FIXES FOR PREVIOUS TEST RESULTS USE QA TRACKING CYCLE 2 TO LOG NEW/ UNRESOLVED TESTS
Test_Number | Test_Name | Test_Description | Test_Steps | Variant | Expected_results | Results
C1 | Overall design implementation | The webStore should match the original design as much as possible throughout the different pages. Not every page and element will have a design to compare against so a bets effort has to be applied. To test compare the available design assets against the webStore in all browsers and langages. | 1. Compare images from 'theme mockups' gainst the active webStore | Offset 10px | The webStore should represent the mockup in it's entirety | Passed
|  |  | 2. Take screen shots and highlight elements that are not matching | Not breaking containers
Passed
C2 | Logo Placement | Check that the banner is in the same place on all pages | 1. Compare against design | Offset 10px | Matches the design within 10px | Passed
Not breaking containers
Passed
C3 | Content Container Titles | Check to make sure all of the content containers have the same sized titles | 1. Compare against design | Font face | Matches the design | similar with the mockup
|  |  |  | Font sizing |  | similar with the mockup
|  |  |  | Font color |  | similar with the mockup
Offset 5px
Passed
C4 | Link Colours | Check that make sure that links are consistent and in line with the design. Check that the hover color is consistent and inline with the design. | 1. Compare against design | Font color | Matches the design | Passed
|  |  |  | Hover color |  | Passed
C5 | Main Menu Sizing | Ensure the Main Menu sizing is consistent with the design, across all browsers, and languages. | 1. Compare against design | Offset 10px | Matches the design
Passed
C6 | Main Menu Hover State | Ensure the Main Menu hover state is consistent with the design, across all browsers, and languages. | 1. Compare against design |  | Matches the design
Passed
C7 | Background Image | Ensure the background image is consistent with the design, across all browsers, and languages. | 1. Compare against design |  | Matches the design
Passed
C8 | Ad Placement | Ensure the Ad placement is consistent with the design, across all browsers, and languages. | 1. Compare against design |  | Matches the design with in 10px
Passed
C9 | Ad colisions | Ensure that Ads are not affected by the implementation of the theme | 1. Compare against design |  | Matches the design with in 10px
C10 | Over all Positioning | Ensure that the positioning of elements are consistent with the design, across all browsers, and languages. | 1. Compare against design |  | Matches the design with in 10px
Passed
C11 | Padding / Margin | Ensure that padding and margins are consistent with the design across all browsers and languages. | 1. Compare against design |  | Matches the design with in 10px
Passed

## Tests - Theme Specific
VISUAL - Theme and Page specific |  | This section is to document theme modification which are specific to a single page or element in e5. If there are no theme or page specific requests there is nothing to test here. |  | DO NOT EDIT THIS PAGE
Notes: THIS PAGE IS A REFERENCE FOR THE TEST CASES DO NOT EDIT THIS PAGE CHECK QA TRACKING 1 FOR FIXES FOR PREVIOUS TEST RESULTS USE QA TRACKING CYCLE 2 TO LOG NEW/ UNRESOLVED TESTS
Test_Number | Test_Name | Test_description | Page_Element_Description | Expected_Outcome
T1 | Top Menu is switched | There is a specific JavaScript to switch the top menu and display the Microsoft HUP | If this is not being loaded properly, the 'Sign in' and 'Language' toggle will be squished in the the 'Home/Account/Help' . The Microsoft HUP logo will also not be present | The banner should be loading and both menu's should be aligned properly with padding | NOTE: If the javascript does not load, it is VERY obvious when it fails!
T2 | Buttons are all styled properly | All of the buttons should match each other and not be defaulting to the standard button styling if there is no CSS present | If there is a button that has 'rounded' corners this is a clear indication that the button is not styled properly. Most buttons should have square corners as per mockup | All buttons should be the same style

## Tests - Scripting
SCRIPTS and ERRORS |  |  |  | DO NOT EDIT THIS PAGE
Notes: THIS PAGE IS A REFERENCE FOR THE TEST CASES DO NOT EDIT THIS PAGE CHECK QA TRACKING 1 FOR FIXES FOR PREVIOUS TEST RESULTS USE QA TRACKING CYCLE 2 TO LOG NEW/ UNRESOLVED TESTS
Test_Number | Test_Name | Test_Description | Test_Steps | Specific_Test_Pages | Expected_results
S1 | onload Javascript Errors | Check that browsers do not throw javascript errors when the page loads. Use 'deveoper' tools to check the console log to check for javascript errors on page load | 1. Open the 'console' |  | No javascript errors should be present
2. Reload page
3. Look for errors in the console
S3 | Get Clicky | There is a 'get clicky' script that runs in the background for analytics. | 1. Open the 'console' |  | No javascript error that references 'get clicky'
2. Reload page
3. Check for javascript that reference 'get clicky'

## Tracking - Cycle 1
QA CYCLE #1
Notes: - QA: Use this page to document issues in columns A - H - Marketing: Use this page to document the fixes to the issues raised by QA : Columns I - J - Submitted : January 24th 2013 - Gaseitsiwe Meyer - Returned : January 28th 2013 - by Jesse Burcsik |  | To be filled out by QA |  | to be filled out by QA | to be filled out by QA | to be filled out by QA | to be filled out by QA | To be filled out by Marketing | To be filled out by Marketing
Reference_Number | Test_Name | Test_Description | Problem_Description | Broken_Page | Page_Path | Results - QA | Results Comments | Fix Ressults | Fix Results Comments
Theme specific | Theme specific | Theme specific
T1 | There is a specific JavaScript to switch the top menu and display the Microsoft HUP | Sign in' and 'Language' toggle will be squished in the the 'Home/Account/Help' . | <problem> | <page> | <url> | <pass/fail> | <comments> | <pass/fail> | <desc>
|  |  |  | Home page |  | Pass |  | Pass
[6 empty] | Fail | Left Ad is pushing all other frames out of the main frame | Pass | (Not an issue fixable on our end)
T2 |  | Left placed Ad moves other frames out of the main frame.(figure 1)
Test constants | Test constants | Test constants
C1 | Overall design implementation | The webStore should match the original design as much as possible throughout the different pages. Not every page and element will have a design to compare against so a bets effort has to be applied. To test compare the available design assets against the webStore in all browsers and langages. | 1.Compare images from 'theme mockups'against the active webstore | Offset 10px |  | Pass |  | Pass
|  |  | 2.Take screen shots and highlight elements that are not matching | Not breaking containers
C2 | Logo Placement | Check that the banner is in the same place on all pages | 1. Compare against design |  |  | Fail | Hup Banner is missing | Pass | This is to be fixed in e5, not through CSS
C3 | Content Container Titles | Check to make sure all of the content containers have the same sized titles | 1. Compare against design | Font face |  | Pass
|  |  |  | Font sizing |  | Pass
|  |  |  | Font color |  | Fail | Solid blue colour is missing(Hup-banner) | Pass | This is to be fixed in e5, not through CSS
Offset 5px
C4 | Link Colours | Check that make sure that links are consistent and in line with the design. Check that the hover color is consistent and inline with the design. | 1. Compare against design | Font color |  | Pass |  | Pass
|  |  |  | Hover color |  | Pass |  | Pass
C5 | Main Menu Sizing | Ensure the Main Menu sizing is consistent with the design, across all browsers, and languages. | 1. Compare against design | Offset 10px |  | Pass |  | Pass
C6 | Main Menu Hover State | Ensure the Main Menu hover state is consistent with the design, across all browsers, and languages. | 1. Compare against design
C7 | Background Image | Ensure the background image is consistent with the design, across all browsers, and languages. | 1. Compare against design |  |  | Pass |  | Pass
Failed
C8 | Ad placement | Left placed Ad moves other frames out of the main frame.(figure 1) | 1. Compare against design |  |  |  | Left Ad is pushing all other frames out of the main frame | Pass | This is an e5 issue
C9 | Ad colisions | Ensure that Ads are not affected by the implementation of the theme | 1. Compare against design |  |  | Fail due to T2
C10 | Over all Positioning | Ensure that the positioning of elements are consistent with the design, across all browsers, and languages. | 1. Compare against design |  |  | Pass
C11 | Padding / Margin | Ensure that padding and margins are consistent with the design across all browsers and languages. | 1. Compare against design |  |  | Pass
Tests Scripting | Tests Scripting | Tests Scripting
S1 | No javascript errors should be present |  | The following warning is available in firefox and Chrome browsers. "Use of getPreventDefault() is deprecated. Use defaultPrevented instead."
[6 empty] | Pass | Despite warnings all works well
S2 | No javascript error that references 'get clicky' |  |  |  |  | Pass | No errors associated to get click
S3

## Tracking - Cycle 2
To be filled out by QA | To be filled out by QA | To be filled out by QA | To be filled out by marketing | To be filled out by marketing
Page_Path | Results - QA | Results Comments | Fix Ressults | Fix Results Comments
Theme specific | Theme specific | Theme specific
T1 | There is a specific JavaScript to switch the top menu and display the Microsoft HUP | Sign in' and 'Language' toggle will be squished in the the 'Home/Account/Help' . | <problem> | <page> | <url> | <pass/fail> | <comments> | <pass/fail> | <desc>
|  |  |  | Home page |  | Pass |  | Pass
[6 empty] | e5 issue | Left Ad is pushing all other frames out of the main frame | Pass | (Not an issue fixable on our end) | Ontime defect
T2 |  | Left placed Ad moves other frames out of the main frame.(figure 1)
Test constants | Test constants | Test constants
C1 | Overall design implementation | The webStore should match the original design as much as possible throughout the different pages. Not every page and element will have a design to compare against so a bets effort has to be applied. To test compare the available design assets against the webStore in all browsers and langages. | 1.Compare images from 'theme mockups'against the active webstore | Offset 10px |  | Pass |  | Pass
|  |  | 2.Take screen shots and highlight elements that are not matching | Not breaking containers
C2 | Logo Placement | Check that the banner is in the same place on all pages | 1. Compare against design |  |  | Talked to Cheryl.Not an issue | Hup Banner is missing | Pass | This is to be fixed in e5, not through CSS
C3 | Content Container Titles | Check to make sure all of the content containers have the same sized titles | 1. Compare against design | Font face |  | Pass
|  |  |  | Font sizing |  | Pass
|  |  |  | Font color |  | Not an issue | Solid blue colour is missing(Hup-banner) | Pass | This is to be fixed in e5, not through CSS
Offset 5px
C4 | Link Colours | Check that make sure that links are consistent and in line with the design. Check that the hover color is consistent and inline with the design. | 1. Compare against design | Font color |  | Pass |  | Pass
|  |  |  | Hover color |  | Pass |  | Pass
C5 | Main Menu Sizing | Ensure the Main Menu sizing is consistent with the design, across all browsers, and languages. | 1. Compare against design | Offset 10px |  | Pass |  | Pass
C6 | Main Menu Hover State | Ensure the Main Menu hover state is consistent with the design, across all browsers, and languages. | 1. Compare against design
C7 | Background Image | Ensure the background image is consistent with the design, across all browsers, and languages. | 1. Compare against design |  |  | Pass |  | Pass
[6 empty] | e5 issue |  |  |  | logged in on time
C8 | Ad placement | Left placed Ad moves other frames out of the main frame.(figure 1) | 1. Compare against design |  |  |  | Left Ad is pushing all other frames out of the main frame | Pass | This is an e5 issue
C9 | Ad colisions | Ensure that Ads are not affected by the implementation of the theme | 1. Compare against design
C10 | Over all Positioning | Ensure that the positioning of elements are consistent with the design, across all browsers, and languages. | 1. Compare against design |  |  | Pass
C11 | Padding / Margin | Ensure that padding and margins are consistent with the design across all browsers and languages. | 1. Compare against design |  |  | Pass
Tests Scripting | Tests Scripting | Tests Scripting
S1 | No javascript errors should be present |  | The following warning is available in firefox and Chrome browsers. "Use of getPreventDefault() is deprecated. Use defaultPrevented instead."
[6 empty] | Pass | Despite warnings all works well
S2 | No javascript error that references 'get clicky' |  |  |  |  | Pass | No errors associated to get click